## Data health
Check | Severity | Result | Rows | Dollars | Detail | Examples
166 classifications have not been confirmed by anybody | warning | FAILS | 166 | 83375674 | Importance, timing and type are proposed by rule until somebody signs off. Until then no chart built on them states a fact. | FIRE-001 FIRE-002 PW-001 WWTP-001 HIGHWAY-001 BLDG-001 BLDG-002 BLDG-003
166 projects do not say how far they can move | error | FAILS | 166 | 83375674 | Earliest and latest year. Without them the scenario engine cannot move anything, and the affordability question cannot be answered. | FIRE-001 FIRE-002 PW-001 WWTP-001 HIGHWAY-001 BLDG-001 BLDG-002 BLDG-003
157 projects disagree with their funding source about the set of books | error | FAILS | 157 | 43684852 | A source belongs to one set of books or the accounting is wrong. Where the project says one thing and its source another, one of them is a typo. | FIRE-001 FIRE-002 PW-001 WWTP-001 HIGHWAY-001 BLDG-001 BLDG-002 BLDG-003
24 projects have no division | warning | FAILS | 24 | 21906764 | Division answers who operates the asset and will do the work. Blank rows drop out of every division cut. | FIRE-001 FIRE-002 FIRE-003 FIRE-004 PARKING-001 FIRE-005 FIRE-006 BLDG-009
1 project names no set of books | error | FAILS | 1 | 20000000 | The money axis is entity then source. A project with no entity files as Not stated and its totals land nowhere. | WWTP-027
6 projects have no funding source identified | warning | FAILS | 6 | 19453322 | An unidentified source is an honest answer and a real number. It is counted here so it cannot disappear into a summary. | PW-009 PZ-001 PZ-002 LIBE-001 TOWN-001 TOWN-002
12 rows are flagged as needing somebody to check them | warning | FAILS | 12 | 2612936 | Rows the register itself marks for verification. | PW-002 PW-004 BLDG-012 PW-019 PARKING-002 BLDG-021 PARKING-003 BLDG-023
2 projects have no department | error | FAILS | 2 | 1003322 | A project with no department cannot be defended at a budget hearing, and does not reconcile against a cost center. | TOWN-001 TOWN-002
1 project carries no cost at all | warning | FAILS | 1 | 0 | A project with no cost is invisible in every total but still occupies a year. | PW-014
Every project has a location | warning | holds | 0 | 0 | Location is what makes a facility life-cycle view possible.
Every project has a useful life | warning | holds | 0 | 0 | Useful life drives the replacement year, the salvage curve and the full-depreciation benchmark.
Funding equals cost, year by year | error | holds | 0 | 0 | Checked, never enforced: a half-entered project is a normal state and a department head has to be able to leave one. The residual reads as unfunded.